## Slide 1
CIAM Support Assistant for L1 Ticket Resolution
Status
Summary
On Track
This week:
1. Refined Agent 1 (Intent Classifier) code to make it more robust, and redeployed it.
2. Jose completed a human review of Agent 1's responses — confirmed the agent's output matches what a human analyst would conclude manually, validating Agent 1 as fully functional in the sandbox environment.
3. Deployed Agent 2 (Database Agent) on Bedrock AgentCore.
4. Building a synthetic/mock DynamoDB dataset to test Agent 2 against, since production data access is not yet approved.
Next week:
1. Test Agent 2 against the synthetic DynamoDB data; debug and fix any response errors to make it fully functional.
2. Design and begin deployment of Agent 3 (Auth0 Agent).
Project Leader
Shristy Jaiswal
Project Manager
Self Managed
Scope Health
Schedule Health
Project Update Date
15/07/26
Project Closure Date
31/07/26
Jira Link
GIS-3793
Confluence Page
netskope.atlassian.net/.../CIAM+Support+Assistant+Project+Charter
Recent Accomplishments
Date
Agent 1 (Intent Classifier) confirmed fully functional — human review validated its responses match manual analysis, in the sandbox environment.
13/07/26
Successfully deployed Agent 2 (Database Agent) on Bedrock AgentCore.
15/07/26
Upcoming Milestones
Date
Status
Make Agent 2 (Database Agent) fully functional — test against synthetic DynamoDB data and debug/fix errors.
22/07/26
Design and begin deployment of Agent 3 (Auth0 Agent).
24/07/26
Risk/Impediments
Mitigation Plan
Risk: AWS Bedrock AgentCore has not yet been approved for production use — without it, agents can't be tested or trained against real, live Netskope data (Auth0, DynamoDB, Confluence); validation so far relies on synthetic/test data.
Mitigation: Requesting approval to connect AgentCore to real production data sources, so accuracy can be validated before rollout to L1.
netskope
2026 © Netskope Confidential. All rights reserved.
1